## Sheet1
Risk ID | Risk Description | Asset | Likelihood | Impact | Risk Score | Risk Level | Risk Owner | Treatment Strategy | Treatment Plan Summary | Linked Control(s) | Status | Review Date
RSK-001 | Unauthorized access to production database | Production DB | 3 | 3 | 9 | High | DevOps Lead | Mitigate | Implement RBAC and MFA | A.9.1.2, A.12.4.1 | Open | 2025-09-30
RSK-002 | Phishing attack targeting employee credentials | Email System | 3 | 2 | 6 | Medium | IT Security | Mitigate | Conduct phishing simulations and awareness training | A.7.2.2, A.12.6.2 | In Progress | 2025-09-15
RSK-003 | Data loss due to lack of backup | File Server | 2 | 3 | 6 | Medium | Infrastructure Lead | Mitigate | Implement daily automated backups with offsite replication | A.12.3.1 | Open | 2025-09-10
RSK-004 | Unpatched software vulnerabilities | Application Stack | 3 | 2 | 6 | Medium | AppSec Team | Mitigate | Enforce monthly patch cycles and vulnerability scanning | A.12.6.1 | Open | 2025-09-20
RSK-005 | Insider threat from privileged user | HR System | 2 | 3 | 6 | Medium | HR Manager | Mitigate | Enable activity logging and conduct background checks | A.9.2.3, A.12.4.3 | Open | 2025-10-01
RSK-006 | Insecure third-party vendor integration | CRM Platform | 2 | 2 | 4 | Medium | Vendor Manager | Transfer | Update contracts to include security SLAs and audits | A.15.1.1, A.15.2.1 | In Progress | 2025-09-25
RSK-007 | Ransomware infection via endpoint | Workstations | 3 | 3 | 9 | High | IT Security | Mitigate | Deploy EDR and restrict admin privileges | A.12.2.1, A.13.2.1 | Open | 2025-09-30
RSK-008 | Misconfigured cloud storage exposing data | Cloud Storage | 2 | 3 | 6 | Medium | Cloud Architect | Mitigate | Enforce encryption and access policies | A.10.1.1, A.13.1.3 | Open | 2025-09-18
RSK-009 | Lack of incident response plan | Entire Org | 2 | 3 | 6 | Medium | CISO | Mitigate | Develop and test IRP quarterly | A.16.1.1, A.16.1.5 | In Progress | 2025-10-05
RSK-010 | Weak password practices | User Accounts | 3 | 2 | 6 | Medium | IT Helpdesk | Mitigate | Enforce password complexity and rotation policies | A.9.2.4 | Open | 2025-09-12